## Risk Assessment
Risk Description | [7 empty] | Pre-Treatment Assessment | [6 empty] | Post-Treatment Assessment
Ref # | Asset Group | Asset | Threat | Vulnerability | Risk Type | Risk Owner | Reassesment Frequency | Existing Controls | Liklihood | Liklihood Rational | Impact | Impact Rational | Risk Score | Risk Level | Treatment Option Chosen | Proposed Treatment Action | Treatment Cost | Treatment Owner | Related Documentation
1 | Information | Customer Database | Unauthorized access to sensitive customer data, including personal information, financial data, and health records. | The Database is accessible by unauthorized external hackers | C | CIO | Quarterly | Server is up to industry standards | 3 | An expoloited vulnerabilty is always a possibility. | 4 | Loss of reputation and trust. Significant fines | 12 | HIGH | Modify | Introduce more effective firewalls and patch systems more often. | $5-10,000 | CIO | Incident Response Plan, Security Policy
2 | Network | Network Storage | Encryption of critical systems and data, demanding a ransom for decryption. | Ransomware Attack encrypts all data on the organizations network | A | CIO | Quarterly | Anti-malware is used and system backups are made regularly. | 3 | Ransomware attacks are more common than ever | 4 | Can result in severe financial and data loss within the company | 12 | HIGH | Modify | Improve Backup security and anti-malware software | 10000 | CIO | Recovery plan
3 | Network | Web Server | Bad actors intentionally clog internet bandwidth to prevent customers from being able to access our web store. | Distributed Denial of Service (DDOS) attacks, halt organizations' network operations. | A | CIO | Quarterly | Availability of web server is monitored regularly | 3 | DDOS attacks are growing in popularity. Even when we arent a specific target | 4 | Employee and Customers unable to access our network can result in loss of revenue for the organization | 12 | HIGH | Accept | Use multiple servers to lessen the load of network traffic on each one. | 20000 | CIO | Network Infrastructure Guidelines
4 | People | Network Storage | Deception tactics to trick employees into revealing sensitive information or clicking on malicious links. | People falling for phishing emails can reveal company log in data or give access to unauthorized users. | CIA | CIO | Quarterly | Basic employee awareness and software that scans for malicious emails | 4 | Phishing attacks are the most common kind of attack and people make mistakes. | 3 | It can vary depending on the severity of the phishing attack. | 12 | HIGH | Modify | Improve employee training and raise awareness about phishing attacks and how to identify them | 5000 | CIO | Phishing Response Policy
5 | Hardware | Network Operations | Hardware or software failures can shut down business operations | Critical systems may be unable to function without specific hardware or software running effectively | CIA | CIO | Bi-Annualy | Hardware and software is regularly updated and inspected | 2 | Depends on the hardware and software life-span. How we treat our systems and chance | 4 | If critical systems fail that it can shut down business operations temporarily | 8 | MEDIUM | Accept | Stay up to date with software and hardware updates and perform inspections more regularly | 2000 | CIO | Business Continuity Plan
6 | Network |  | Internet Availability may be unreliable at times and cause network outages | Power outage or networks down can leave an organization unable to access systems and perform operations | A | CIO | Anually | Backup network systems and generators in case of outage | 1 | Not very likely for networks to go down based on business locations | 3 | Without internet access or power. Business may be unable to continue business operations or access systems | 3 | LOW | Accept | Keep generators functioning properly and ensure that backup systems are properly configured | 10000 | CIO | Disaster Recovery Plan,
7 | Information |  | Unclear Incident response and disaster recovery plans can make it so that responses are ineffective or slow | Information security responsibilities are not clearly defined | CIA | CISO | Bi-Annualy | IT service desk is the go-to solution for problems | 3 | No set course of action | 3 | We would be able to respond to incidents but the response would be slow and could lead to increases in loss | 9 | MEDUIM | Modify | Update Disaster recovery, incident response and business continuity plans to cover all possible scenarios | 5000 | CISO | Incident Response Plan, Business Impact Policy
8 | People |  | Employee is recruited who could intentionally breach information security | Background checks and employee hiring process it too trust worthy | CIA | HR | Anually | Basic background checks and employee references | 2 | Employees are most likely not going to be a threat to the company hiring them for our business | 3 | It depends on how quickly employee is caught and their level of clearance in the company | 6 | MEDIUM | Modify | Update employement process with HR and make sure that future employees pass intensive background checks and employment history | 3000 | HR Manager | Onboarding Procedures, Access Control Policy
9
10

## Assessment Details
Asset Based Risk Assessment Tool
Assessment Details
Security Classification | Confidential
Risk Assessment Title | Organization wide initial risk assessment
Risk Assessment Scope | All business activities, locations and facilities are in the scope.
Context of Risk Assessment | As part of obtaining certification to the ISO27001 standard for information security, this risk assessment has been carried out to set a baseline for future work, and to identify the major risks the organization currently faces, particularly with regard to Internet-facing services
Risk Acceptance Criteria | Low risks will be accepted. All other ranked risks will be at the discretion of the risk owner and top management
Version | 1
Dated | 2024-11-10
Risk Assessors | Lead Assessor - Julian VanDevented
Risk Assessment Participants | CIO, CISO
Approval | CEO
Date Approved | 2024-11-10